## Project Summary
Week | Task | Description | Time Spent (hrs) | Weekly Total
2/22 - 2/25 | Research | Reviewed project proposal and noted any questions for sponsor meeting | 11 | 46.5
| Team Meeting | Introductions, determine schedule for semester | 8
| Sponsor Meeting | Discussed previous sponsor meeting and distributed work, developed plan | 10
| Vison Document | Started work on Vision Document | 13.5
2/26 - 3/4 | Research | Studied template documents | 7 | 65
| Team Meeting | Briefly updated team on each member's progress | 2
| Sponsor Meeting | Discussed broad overview of project | 6
| Programming | Started work on Programming | 40
3/5 - 3/11 | Research | Reviewed new sponsor-provided documents | 8 | 57
| Team Meeting | Briefly updated team on each member's progress | 2
| Research | Met to discuss the documents provided by sponsor | 4
| Programming | Continued work on section Sign-up | 37
3/12 - 18 | Research | Checked sponsor documents/notes against our documents for correctness | 12 | 46
| Team Meeting | Briefly updated team on each member's progress | 2
| Programming | Continued work on section Sign-up | 26
3/19 - 3/22 | Research | Checked android studios tutorials to gain better understanding to make app | 20 | 86.5
| Sponsor Meeting | Met with sponsor to define goals | 6.5
| Programming | Continued work on section Sign-up | 57
Total Team Hours
381.5
Average Team Hours/Week
54.5
Note on A1: Modify the week column for 2017 Spring
Note on B1: Delete the following sample tasks and write your team tasks!
Note on C1: Delete the following sample tasks descriptions and write your own descriptions!
Note on D1: Revise the numbers based on your performance time for each task.
Note on E1: Update the formula based on your time spent for each week.

## Tyler Cole
Week | Task | Description | Time Spent (hrs) | Weekly Total
2/22 - 2/25 | Team Meeting | Weekly meeting with team to review progress and define Sprint2, distributed work, developed plan | 1.5 | 1.5
| Sponsor Meeting | Met with sponsor to review requirements for project | 0.5
2/26 - 3/4 | Sponsor Meeting | Discussed broad overview of project | 0.5 | 5.5
| Team Meeting | Met with team to discuss progress and challenges of current project's state. | 1
| Research | Cursory research on Maps API for "Show current map to users" | 2
| Coding | Created seperate test environment. "Show current map to users" worked on. | 2
3/5 - 3/11 | Research | Research on camera and MyLocation for "center map on user location" task. | 3 | 16.5
| Coding | Code written in a seperate testing environment. "Center map os user user location" worked on. | 12
| Team Meeting | Met with team to discuss progress and challenges of current project's state. | 1
| Sponsor Meeting | Discussed broad overview of project | 0.5
3/12 - 18 | Research | These tasks done in tandem. Research on Markers and InfoWindows for "display content to users" task. Code written in a seperate app testing environment. | 5 | 21
| Coding | Code written in a seperate testing environment. "Display content to users" worked on. | 15
| Team Meeting | Briefly updated team on each member's progress | 1
3/19 - 3/22 | Team Meeting | Spoke with Lily and Rudi about project database | 4 | 17
| Team Meeting | Provided help with Lily's code | 4
| Team Meeting | All met to update docs | 1
| Research | Troubleshooting integration errors | 3
| Coding | Integrating code from seperate environment to app. | 5
Total Team Hours
62
Average Hours/Week
12.4
Note on A1: Modify the week column for 2017 Spring
Note on B1: Delete the following sample tasks and write your team tasks!
Note on C1: Delete the following sample tasks descriptions and write your own descriptions!
Note on D1: Revise the numbers based on your performance time for each task.
Note on E1: Update the formula based on your time spent for each week.

## Rudi Wever
Week | Task | Description | Time Spent (hrs) | Weekly Total
2/22 - 2/28 | Research/Coding | Reviewed tutorial on Camera2 and coded initial Camera2 activity (2 days) | 20 | 24
| Team Meeting | Weekly meeting with team to review progress and define Sprint2, distributed work, developed plan | 1.5
| Sponsor Meeting | Met with sponsor to review requirements for project | 0.5
| Travel | Went to 2 libraries to find additional resources about Android apps/ Android Camera | 2
3/1 - 3/7 | Research/Coding | Reviewed additional tutorials on Camera2 for photo capture and video capture and coded more advanced secondary Camera2 activity (6 days) | 41 | 42.5
| Sponsor Meeting | Discussed broad overview of project | 0.5
| Team Meeting | Met with team to discuss progress and challenges of current project's state. | 1
3/8 - 3/14 | Research/Coding | Reviewed additional tutorials on Camera2 to develop additional camera2 functions: custom chronometer, switch front/rear cameras, access and present camera roll. (6 days) | 43 | 44.5
| Team Meeting | Met with team to discuss progress and challenges of current project's state. | 1
| Sponsor Meeting | Discussed broad overview of project | 0.5
3/15 - 3/22 | Research/Coding | Reviewed requirements for registration of user to app/ redesigned User class for greater access throughout all app activities. Implemented changes throughout activities. Researched and implemented 3-way toggle for flash icons. Researched and implemented flash capabilities for Camera2 activity. (6 days) | 42 | 48
| Team Meeting | Briefly updated team on each member's progress | 1
| Team Assistance | Assisted team member on additional camera functionality for flash capability | 5
| Team Meeting | Briefly updated team on each member's progress | 2.5
| Charter | Work on sections | 12
| Plan | Work on sections | 14
Total Team Hours
187.5
Average Team Hours/Week
37.5
Note on A1: Modify the week column for 2017 Spring
Note on B1: Delete the following sample tasks and write your team tasks!
Note on C1: Delete the following sample tasks descriptions and write your own descriptions!
Note on D1: Revise the numbers based on your performance time for each task.
Note on E1: Update the formula based on your time spent for each week.

## Anthony Kowal
Week | Task | Description | Time Spent (hrs) | Weekly Total
2/22 - 2/25 | Team Meeting | Weekly meeting with team to review progress and define Sprint2, distributed work, developed plan | 1.5 | 1.5
| Sponsor Meeting | Met with sponsor to review requirements for project | 0.5
2/26 - 3/4 | Sponsor Meeting | Discussed broad overview of project | 0.5 | 19.5
| Team Meeting | Met with team to discuss progress and challenges of current project's state. | 1
| Research | Research on Camera (4 Days) #66 / #65 / #75 | 9
| Coding | Work with tutorials to lean how Camera API works (5 Days) #66 / #65 / #75 | 9
3/5 - 3/11 | Research | Research on camera and for how to make Flash work | 4 | 13.5
| Coding | Work with tutorials to lean how Flash works (2 Days) #66 | 8
| Team Meeting | Met with team to discuss progress and challenges of current project's state. | 1
| Sponsor Meeting | Discussed broad overview of project | 0.5
3/12 - 18 | Research | These tasks done in tandem. Research on Camera2 API and look into filters | 10 | 26
| Coding | Work with tutorials to lean how Flash works with Camera2 API (5 Days) #66 | 15
| Team Meeting | Briefly updated team on each member's progress | 1
3/19 - 3/22 | Team Meeting | Spoke with Rudi on help with code to understand my issue with Flash | 2 | 5.5
| Team Meeting | All met to update docs | 1
| Research | Troubleshooting view issues with .xml of camera | 0.5
| Coding | Further coding for layer filter #65 | 2
Total Team Hours
66.5
Average Hours/Week
13.3
Note on A1: Modify the week column for 2017 Spring
Note on B1: Delete the following sample tasks and write your team tasks!
Note on C1: Delete the following sample tasks descriptions and write your own descriptions!
Note on D1: Revise the numbers based on your performance time for each task.
Note on E1: Update the formula based on your time spent for each week.

## Lilith Matthews
Week | Task | Description | Time Spent (hrs) | Weekly Total
2/22 - 2/25 | Team Meeting | Weekly meeting with team to review progress and define Sprint2, distributed work, developed plan | 1.5 | 14
| Sponsor Meeting | Talk about progress, demo current project | 0.5
| Research | Nexmo activity for task 76 | 12
2/26 - 3/4 | Research | Nexmo Activity for Task 76 | 6 | 13.5
| Sponsor Meeting | Discussed broad overview of project | 0.5
| Team Meeting | Briefly updated team on each member's progress | 1
| Code | Nexmo Activity for Task 76 | 6
3/5 - 3/11 | Spring Break | Spring Break |  | 10
| Research | General Android API research | 10
3/12 - 18 | Research | Nexmo API and Tutorial for Task 76 | 4 | 11
| Team Meeting | Briefly updated team on each member's progress | 1
| Code | Nexmo Tutorial for Task 76 | 6
3/19 - 3/22 | Team Meeting | Spoke with Tyler and Rudi about project database | 4 | 17
| Code | Log In with Username not Email task 76 | 4
| Team Meeting | All met to update docs | 1
| Code | Nexmo Activity for Task 76 | 8
Total Team Hours
65.5
Average Team Hours/Week
13.1
Note on A1: Modify the week column for 2017 Spring
Note on B1: Delete the following sample tasks and write your team tasks!
Note on C1: Delete the following sample tasks descriptions and write your own descriptions!
Note on D1: Revise the numbers based on your performance time for each task.
Note on E1: Update the formula based on your time spent for each week.