## Project Summary
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/08 - 1/14 | Research | Reviewed project proposal and noted any questions for sponsor meeting | 11 | 46.5
| Team Meeting | Introductions, determine schedule for semester | 8
| Sponsor Meeting | Discussed previous sponsor meeting and distributed work, developed plan | 10
| Setup Tools | Created groups for Slack, Taiga, GitHub | 4
| Vison Document | Started work on Vision Document | 13.5
1/15 - 1/21 | Research | Studied template documents | 7 | 65
| Sponsor Meeting | Discussed broad overview of project | 6
| Vison Document | Finished work on section | 12
| Programming | Started work on Programming | 40
1/22 - 1/28 | Research | Reviewed new sponsor-provided documents | 8 | 57
| Design | Constructed Wire-Frame Mockup of design provided by sponsor | 8
| Research | Met to discuss the documents provided by sponsor | 4
| Programming | Continued work on section Sign-up | 37
1/29 - 2/03 | Research | Checked sponsor documents/notes against our documents for correctness | 12 | 46
| Team Meeting | Briefly updated team on each member's progress | 2
| Vison Document Upgrade | Continued work on section | 6
| Programming | Continued work on section Sign-up | 26
2/05 - 2/11 | Research | Checked android studios tutorials to gain better understanding to make app | 20 | 86.5
| Sponsor Meeting | Met with sponsor to define goals | 6.5
| Vison Document Upgrade | Finished work on section | 3
| Programming | Continued work on section Sign-up | 57
2/12 - 2/18 | Research | Checked android studios tutorials to gain better understanding to make app | 12 | 95
| Team Meeting | Reviewed app progress | 5
| Programming | Continued work on section Sign-up | 78
Total Team Hours
396
Average Team Hours/Week
66

## AJ Kowal
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/08 - 1/14 | Research | Reviewed project proposal and noted any questions for sponsor meeting | 3 | 12
| Team Meeting | Introductions, determine schedule for semester | 2
| Sponsor Meeting | Discussed previous sponsor meeting and distributed work, developed plan | 2
| Setup Tools | Created groups for Slack, Taiga, GitHub | 1
| Vison Document | Started work on Vision Document | 4
1/15 - 1/21 | Research | Studied template documents | 3 | 11.5
| Sponsor Meeting | Discussed broad overview of project | 1.5
| Vison Document | Finished work on section | 3
| Programming | Started work on Programming | 4
1/22 - 1/28 | Research | Reviewed new sponsor-provided documents | 2 | 9
| Research | Met to discuss the documents provided by sponsor | 1
| Programming | Continued work on section Sign-up | 6
1/29 - 2/03 | Research | Checked sponsor documents/notes against our documents for correctness | 3 | 9.5
| Team Meeting | Briefly updated team on each member's progress | 0.5
| Vison Document Upgrade | Continued work on section | 3
| Programming | Continued work on section Sign-up | 3
2/05 - 2/11 | Research | Checked android studios tutorials to gain better understanding to make app | 5 | 10.5
| Sponsor Meeting | Met with sponsor to define goals | 1.5
| Vison Document Upgrade | Finished work on section | 2
| Programming | Continued work on section Sign-up | 2
2/12 - 2/18 | Research | Checked android studios tutorials to gain better understanding to make app | 3 | 11
| Team Meeting | Reviewed app progress | 1
| Programming | Continued work on section Sign-up | 7
Total Hours
63.5
Average Hours/Week
10.5833

## Lilith Matthews
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/08 - 1/14 | Research | Reviewed project proposal and noted any questions for sponsor meeting | 4 | 15
| Team Meeting | Introductions, determine schedule for semester | 2
| Sponsor Meeting | Discussed previous sponsor meeting and distributed work, developed plan | 4
| Setup Tools | Created groups for Slack, Taiga, GitHub | 1
| Vison Document | Started work on Vision Document | 4
1/15 - 1/21 | Research | Studied template documents | 1 | 7.5
| Sponsor Meeting | Discussed broad overview of project | 1.5
| Vison Document | Finished work on section | 2
| Programming | Started work on Programming | 3
1/22 - 1/28 | Research | Reviewed new sponsor-provided documents | 2 | 8
| Research | Met to discuss the documents provided by sponsor | 1
| Programming | Continued work on section Sign-up | 5
1/29 - 2/03 | Research | Checked sponsor documents/notes against our documents for correctness | 3 | 5.5
| Team Meeting | Briefly updated team on each member's progress | 0.5
| Vison Document Upgrade | Continued work on section | Completed
| Programming | Continued work on section Sign-up | 2
2/05 - 2/11 | Research | Checked android studios tutorials to gain better understanding to make app | 5 | 8.5
| Sponsor Meeting | Met with sponsor to define goals | 1.5
| Vison Document Upgrade | Finished work on section | Completed
| Programming | Continued work on section Sign-up | 2
2/12 - 2/18 | Research | Checked android studios tutorials to gain better understanding to make app | 2 | 14
| Team Meeting | Reviewed app progress | 1
| Programming | Continued work on section Sign-up | 11
Total Hours
58.5
Average Hours/Week
9.75

## Rudi Wever
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/08 - 1/14 | Research | Reviewed project proposal and noted any questions for sponsor meeting | 3 | 12.5
| Team Meeting | Introductions, determine schedule for semester | 2
| Sponsor Meeting | Discussed previous sponsor meeting and distributed work, developed plan | 2
| Setup Tools | Created groups for Slack, Taiga, GitHub | 1
| Vison Document | Started work on Vision Document | 4.5
1/15 - 1/21 | Research | Studied template documents | 2 | 37.5
| Sponsor Meeting | Discussed broad overview of project | 1.5
| Vison Document | Finished work on section | 6
| Programming | Started work on Programming | 28
1/22 - 1/28 | Research | Reviewed new sponsor-provided documents | 2 | 33
| Research | Met to discuss the documents provided by sponsor | 1
| Design | Constructed Wire-Frame Mockup of design provided by sponsor | 8
| Programming | Continued work on section Sign-up | 22
1/29 - 2/03 | Research | Checked sponsor documents/notes against our documents for correctness | 3 | 27.5
| Team Meeting | Briefly updated team on each member's progress | 0.5
| Vison Document Upgrade | Continued work on section | 3
| Programming | Continued work on section Sign-up | 21
2/05 - 2/11 | Research | Checked android studios tutorials to gain better understanding to make app | 5 | 57
| Sponsor Meeting | Met with sponsor to define goals | 2
| Vison Document Upgrade | Finished work on section | 1
| Programming | Continued work on section Sign-up | 49
2/12 - 2/18 | Research | Checked android studios tutorials to gain better understanding to make app | 4 | 63
| Team Meeting | Reviewed app progress | 2
| Programming | Continued work on section Sign-up | 57
Total Hours
230.5
Average Hours/Week
38.4167

## Tyler Cole
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/08 - 1/14 | Research | Reviewed project proposal and noted any questions for sponsor meeting | 1 | 7
| Team Meeting | Introductions, determine schedule for semester | 2
| Sponsor Meeting | Discussed previous sponsor meeting and distributed work, developed plan | 2
| Setup Tools | Created groups for Slack, Taiga, GitHub | 1
| Vison Document | Started work on Vision Document | 1
1/15 - 1/21 | Research | Studied template documents | 1 | 8.5
| Sponsor Meeting | Discussed broad overview of project | 1.5
| Vison Document | Finished work on section | 1
| Programming | Started work on Programming | 5
1/22 - 1/28 | Research | Reviewed new sponsor-provided documents | 2 | 7
| Research | Met to discuss the documents provided by sponsor | 1
| Programming | Continued work on section Sign-up | 4
1/29 - 2/03 | Research | Checked sponsor documents/notes against our documents for correctness | 1 | 1.5
| Team Meeting | Briefly updated team on each member's progress | 0.5
2/05 - 2/11 | Research | Checked android studios tutorials to gain better understanding to make app | 5 | 10.5
| Sponsor Meeting | Met with sponsor to define goals | 1.5
| Programming | Continued work on section Sign-up | 4
2/12 - 2/18 | Research | Checked android studios tutorials to gain better understanding to make app | 3 | 7
| Team Meeting | Reviewed app progress | 1
| Programming | Continued work on section Sign-up | 3
Total Hours
41.5
Average Hours/Week
6.9167